## GSD Master Tracker
# | Priority | Category | Area | Issue / Task | Current State | Required Action | Status | Effort | Impact | Owner | Due Date | Verified? | Notes
1 | P0 | Security | Scanner + Marketing | VITE_QR_SIGNING_SECRET exposed client-side | CRITICAL - Secret in browser JS | Move to Supabase Edge Function; scanner sends token+sig to server for validation | NOT STARTED | 1 day | Critical |  |  | NO | Attacker can forge QR codes with this secret
2 | P0 | Payment | Ticket Purchase Site | Stripe in test mode (pk_test_ / sk_test_) | EXPOSED - Not production | Switch to production Stripe keys in Vercel env vars | NOT STARTED | 1 day | Critical |  |  | NO | No real payments possible until switched
3 | P0 | Security | Webhook (Edge Fn) | ALLOWED_ORIGINS not set for production | Defaults to * (any origin) | Set ALLOWED_ORIGINS env var with production domains | NOT STARTED | 1 day | Critical |  |  | NO | Webhook accepts requests from any origin
4 | P0 | DevOps | GitHub Actions | CI/CD pipeline disabled (needs secrets) | DISABLED | Add GitHub Secrets (SUPABASE keys, Stripe keys, Vercel tokens) | NOT STARTED | 1 day | High |  |  | NO | No automated builds, tests, or deploys
5 | P0 | Security | Supabase RLS | Anon access on VIP reservation data | EXPOSED | Audit RLS policies; remove anon SELECT on vip_reservations | NOT STARTED | 1 day | High |  |  | NO | Anyone could query VIP booking data
6 | P0 | Auth | Scanner Site | Dashboard routes not protected at route level | SIDEBAR-ONLY filtering | Add ProtectedRoute wrapper that checks role before rendering; redirect to /auth if unauthorized | NOT STARTED | 2 days | Critical |  |  | NO | /events, /analytics, /team accessible by direct URL
7 | P0 | Auth | Scanner Site | No separate owner vs employee login flow | Single /auth page with demo buttons | Create dedicated login: owner uses email/password; employees use PIN or simple code; remove demo shortcuts | NOT STARTED | 3 days | Critical |  |  | NO | User specifically requested separate logins
8 | P0 | Auth | Scanner Site | Demo/test shortcuts on auth page | EXPOSED in production | Remove 'Employee/Owner/Demo' quick-access buttons; gate behind dev-only flag | NOT STARTED | 1 day | High |  |  | NO | Anyone can click 'Owner' button and access dashboard
9 | P0 | Auth | Scanner Site | localStorage auth fallback can leak to production | Falls back if Supabase not configured | Add NODE_ENV check; disable localStorage auth in production builds entirely | NOT STARTED | 1 day | High |  |  | NO | If env vars missing in prod, auth bypassed
10 | P1 | Dashboard | Owner Dashboard | Revenue trend percentages are hardcoded (12.5%, 8.2%, -3.1%) | HARDCODED | Calculate actual week-over-week and month-over-month deltas from real ticket data | NOT STARTED | 1 day | Medium |  |  | NO | Only fake numbers in entire dashboard
11 | P1 | Dashboard | Owner Dashboard | ticket_count on orders always shows 0 | NOT STORED on orders table | Add ticket_count column to orders OR join tickets table in query | NOT STARTED | 1 day | Medium |  |  | NO | RecentPurchases shows 0 tickets per order
12 | P1 | Dashboard | Owner Dashboard | ticket_type on orders always shows 'General' | NOT STORED on orders table | Store primary ticket_type on order creation OR join ticket_types in query | NOT STARTED | 1 day | Medium |  |  | NO | Can't distinguish VIP vs GA in order list
13 | P1 | Dashboard | Owner Dashboard | Staff performance uses raw user_id, not names | NO USER PROFILES joined | Join users/profiles table to show actual staff names in leaderboard | NOT STARTED | 1 day | Medium |  |  | NO | Dashboard shows UUIDs instead of names
14 | P1 | Dashboard | Owner Dashboard | Real-time subscription refetches ENTIRE dashboard | PERFORMANCE concern | Subscribe to specific tables; only update affected metrics on change | NOT STARTED | 2 days | Medium |  |  | NO | Every scan/order triggers full dashboard reload
15 | P1 | Dashboard | Advanced Analytics | Too many tabs and metrics for a nightclub owner | OVERLY COMPLEX | Simplify to 3 views: Money (revenue/orders), Attendance (scans/capacity), Staff (performance) | NOT STARTED | 2 days | Medium |  |  | NO | Owner wants: how much money? how full? who's working?
16 | P1 | Scanner | Ticket Scanner | No event date awareness - doesn't know tonight's event | MANUAL selection only | Auto-detect active event from server (event_date = today); default to it; warn on date mismatch | NOT STARTED | 2 days | High |  |  | NO | Staff could scan last month's tickets
17 | P1 | Scanner | Ticket Scanner | Event dropdown doesn't show dates | NAME ONLY | Show format: 'Friday Night - Feb 14' in dropdown | NOT STARTED | 1 day | Medium |  |  | NO | Staff picks wrong week's event
18 | P1 | Scanner | Ticket Scanner | Offline mode accepts unknown tickets | ACCEPTS with warning | Change to REJECT unknown tickets offline; only accept cached valid tickets | NOT STARTED | 1 day | High |  |  | NO | Invalid tickets get through the door
19 | P1 | Scanner | Ticket Scanner | Failed scans not logged to server scan_logs | LOCAL ONLY | Log all scan attempts (success AND failure) with rejection reason to scan_logs | NOT STARTED | 1 day | High |  |  | NO | Can't audit rejections or fraud attempts
20 | P1 | Scanner | Ticket Scanner | QR codes without signatures still accepted | NOT ENFORCED | Reject QR codes without valid HMAC signature when signing is enabled | NOT STARTED | 1 day | High |  |  | NO | Counterfeit plain QR codes bypass anti-forgery
21 | P1 | Scanner | Ticket Scanner | No rate limiting on manual entry | UNLIMITED | Add per-scanner rate limit: max 1 scan per second | NOT STARTED | 1 day | Medium |  |  | NO | Fraudster could spam different codes
22 | P1 | Scanner | Ticket Scanner | No device ID shown to staff | HIDDEN in localStorage | Show device name/ID in scanner settings or bottom nav | NOT STARTED | 1 day | Low |  |  | NO | Can't identify which door scanner generated a scan
23 | P1 | VIP | VIP Floor Plan | Floor plan is visual only - no drag-drop positioning | STATIC LAYOUT | Either: (a) add drag-drop with position persistence, or (b) remove floor plan and use simple table list | NOT STARTED | 3 days | Medium |  |  | NO | Tables in hardcoded positions, can't be rearranged
24 | P1 | VIP | VIP Reservations | Invite links require manual copy-paste sharing | MANUAL | Add 'Send Invite' button that opens email/SMS compose with pre-filled invite URL | NOT STARTED | 2 days | Medium |  |  | NO | Staff must manually copy URL and text it to customer
25 | P1 | VIP | VIP Tables | VIP table sync to purchase site not explicitly called | IMPLICIT via event sync | Add explicit VIP table sync call after table creation/update | NOT STARTED | 1 day | Medium |  |  | NO | VIP changes may not propagate to purchase site
26 | P1 | Events | Event Management | Hardcoded fallback events on marketing site | FAKE DATA shown on error | Remove hardcoded events; show proper error state or empty state instead | NOT STARTED | 1 day | Medium |  |  | NO | If DB query fails, shows fake events
27 | P1 | Code Quality | Ticket Purchase Site | orders-service.ts is 2,600 lines | MONOLITHIC | Split into: order-creation.ts, payment-processing.ts, email-handler.ts, ticket-generation.ts | NOT STARTED | 3 days | High |  |  | NO | Unmaintainable single file
28 | P1 | Code Quality | Ticket Purchase Site | AuthContext.tsx is 840 lines | MONOLITHIC | Split into: SessionProvider, ProfileProvider, TwoFactorProvider | NOT STARTED | 2 days | Medium |  |  | NO | Too many concerns in one context
29 | P1 | Code Quality | Scanner Site | 150+ components in flat src/components/ | NO ORGANIZATION | Organize into feature folders: scanner/, dashboard/, vip/, admin/, monitoring/, ui/ | NOT STARTED | 2 days | Medium |  |  | NO | Hard to find components
30 | P1 | Code Quality | Marketing Site | TypeScript strict mode disabled | WEAK TYPES | Enable noImplicitAny and strictNullChecks in tsconfig | NOT STARTED | 2 days | Medium |  |  | NO | Type errors not caught at compile time
31 | P1 | SEO | Marketing Site | No sitemap.xml, robots.txt, or structured data | MISSING | Add sitemap.xml, robots.txt, and JSON-LD structured data for events | NOT STARTED | 1 day | Medium |  |  | NO | Google can't index the site optimally
32 | P2 | Security | Database | PII stored in plaintext (email, phone, names) | NOT ENCRYPTED | Add column-level encryption for customer PII fields | NOT STARTED | 3 days | Medium |  |  | NO
33 | P2 | Performance | Dashboard | No materialized views for analytics queries | LIVE TABLE queries | Create materialized views for revenue/attendance aggregations | NOT STARTED | 2 days | Medium |  |  | NO | Slow under high load
34 | P2 | Performance | All Sites | No image optimization or CDN pipeline | RAW IMAGES | Add image compression (WebP), responsive sizes, CDN caching | NOT STARTED | 2 days | Medium |  |  | NO
35 | P2 | Feature | Marketing Site | Restaurant cart has no payment processing | CART ONLY | Integrate Stripe for food orders OR remove cart feature | NOT STARTED | 5 days | High |  |  | NO | Users can add food to cart but can't pay
36 | P2 | Feature | Ticket Purchase Site | No ticket transfer between customers | MISSING | Add transfer flow: original buyer initiates, new buyer accepts, QR regenerated | NOT STARTED | 5 days | Low |  |  | NO
37 | P2 | Testing | All Sites | k6 load tests configured but not automated | MANUAL | Add load tests to CI/CD pipeline on staging deploys | NOT STARTED | 2 days | Medium |  |  | NO
38 | P2 | Scanner | Ticket Scanner | No batch scan mode for group tickets | INDIVIDUAL ONLY | Add 'Scan Group' mode: check in all tickets in an order at once | NOT STARTED | 3 days | Medium |  |  | NO | Slow for 10-person group
39 | P2 | Scanner | Ticket Scanner | No real-time capacity tracking in scanner UI | MISSING | Show 'X / Y guests inside' with red warning at 90% capacity | NOT STARTED | 2 days | High |  |  | NO | Door staff can't see if venue is full
40 | P2 | Scanner | Ticket Scanner | CheckInCounter runs 2 separate queries | PERFORMANCE | Create single count query or cached RPC function | NOT STARTED | 1 day | Low |  |  | NO
41 | P3 | Feature | All Sites | No bilingual support (EN/ES) | ENGLISH ONLY | Add i18n framework (react-i18next) with Spanish translations | NOT STARTED | 5 days | Medium |  |  | NO
42 | P3 | Compliance | All Sites | No WCAG accessibility audit | NOT AUDITED | Run axe-core audit; fix contrast, labels, keyboard nav | NOT STARTED | 3 days | Medium |  |  | NO
43 | P3 | Feature | All Sites | No public API for third parties | MISSING | Build REST API with API keys for promoters/partners | NOT STARTED | 10 days | Low |  |  | NO
44 | P3 | Feature | Scanner | No weather-triggered door policies | MISSING | Pull weather API; show coat check / VIP parking prompts | NOT STARTED | 2 days | Low |  |  | NO
45 | P3 | Feature | Scanner | No post-scan upsell workflow | MISSING | After green overlay: show quick buttons for table upgrade, bar credit | NOT STARTED | 3 days | Low |  |  | NO
46 | P0 | Auth Setup | Scanner Site (Supabase) | Create owner account in Supabase Auth | NOT CONFIGURED | Create user info@magueynightclub.com with password MagueyNightclub123, set user_metadata.role='owner' | NOT STARTED | 1 hr | Critical |  |  | NO | Required for owner dashboard access
47 | P0 | Auth Setup | Scanner Site (Supabase) | Create employee/scanner account in Supabase Auth | NOT CONFIGURED | Create user Luismbadillo13@gmail.com with password MagueyScanner123, set user_metadata.role='employee' | NOT STARTED | 1 hr | Critical |  |  | NO | Required for scanner access; sample credential — switch to real later
48 | P0 | Auth Setup | Scanner Site | Wire AuthContext to use Supabase credentials | MOCK/DEMO fallback active | Update AuthContext to authenticate against Supabase Auth; remove demo button auto-login; validate role from user_metadata | NOT STARTED | 2 days | Critical |  |  | NO | Login must use real Supabase auth, not localStorage mock
49 | P1 | Credentials | All Sites (.env) | Verify all .env files have consistent Supabase credentials | CONFIGURED but unverified | Confirm VITE_SUPABASE_URL and VITE_SUPABASE_ANON_KEY match across all 3 sites; verify service role key only on server-side | NOT STARTED | 1 hr | High |  |  | NO | Mismatch could cause silent auth failures
50 | P1 | Credentials | Ticket Purchase Site | Verify Stripe test keys are functional | TEST MODE (pk_test_ / sk_test_) | Run test checkout with current Stripe test keys; confirm webhook secret matches Stripe dashboard | NOT STARTED | 1 hr | High |  |  | NO | Keys configured but never end-to-end tested
51 | P1 | Credentials | Ticket Purchase Site | Verify Resend email API key is active | CONFIGURED (re_jH2HNEMf_...) | Send test email via Resend; confirm tickets@tickets.magueynightclub.com domain is verified | NOT STARTED | 1 hr | Medium |  |  | NO | Email won't deliver if domain not verified in Resend
52 | P1 | Credentials | Vercel Deployment | Set all environment variables in Vercel | LOCAL ONLY | Add all env vars (Supabase, Stripe, Resend, QR secret) to Vercel project settings for each site | NOT STARTED | 1 hr | High |  |  | NO | Production deploys will fail without env vars

## What Works (Verified)
# | Area | Feature | Status | Connected To | Data Source | Verified? | Notes
1 | Owner Dashboard | Revenue metrics (today/week/month/all-time) | WORKING | Supabase tickets table | Real ticket prices | YES | All calculated from real data
2 | Owner Dashboard | Real-time updates via Supabase subscriptions | WORKING | tickets, orders, scan_logs | Postgres Changes | YES | Auto-refreshes on any change
3 | Owner Dashboard | Check-in progress per event | WORKING | tickets table (scanned_at) | Real scan data | YES | X/Y checked in format
4 | Owner Dashboard | Upcoming events with capacity % | WORKING | events + ticket_types | Real inventory | YES | Shows sold/capacity ratio
5 | Owner Dashboard | Email delivery status | WORKING | email_queue table | Real queue data | YES | Delivered/pending/failed counts
6 | Owner Dashboard | Scanner device heartbeats | WORKING | scanner_heartbeats table | Real device data | YES | Online/offline status
7 | Owner Dashboard | Order management (search/filter/status) | WORKING | orders table | Real order data | YES | Full CRUD with real-time
8 | Ticket Purchase | Stripe Checkout Sessions (GA tickets) | WORKING | Stripe API + orders table | Edge Function | YES | Server-side pricing, PCI compliant
9 | Ticket Purchase | VIP table payment intents | WORKING | Stripe API + vip_reservations | Edge Function | YES | Atomic booking + pass generation
10 | Ticket Purchase | Webhook signature verification | WORKING | stripe-webhook Edge Function | HMAC-SHA256 | YES | Constant-time comparison
11 | Ticket Purchase | Idempotent webhook processing | WORKING | check_webhook_idempotency RPC | Stripe event ID | YES | Prevents duplicate orders
12 | Ticket Purchase | Circuit breaker for Stripe | WORKING | circuit-breaker.ts | Application-level | YES | 5 failures → open, 30s cooldown
13 | Ticket Purchase | Rate limiting | WORKING | orders-service.ts | Token bucket | YES | 100/min per IP, 50/min per user
14 | Ticket Purchase | QR code generation with HMAC | WORKING | create_order_with_tickets_atomic | HMAC-SHA256 | YES | Unique signed token per ticket
15 | Ticket Purchase | Email confirmation via queue | WORKING | email_queue + Resend API | Server-side | YES | Non-blocking, retry with backoff
16 | Ticket Purchase | Atomic inventory management | WORKING | check_and_reserve_tickets RPC | FOR UPDATE locks | YES | Prevents overselling
17 | Ticket Purchase | Event sourcing audit trail | WORKING | ticket_events table | Immutable log | YES | Full ticket lifecycle
18 | Ticket Purchase | Promo code system | WORKING | promo_codes table | Database-backed | YES | Validation + discount calculation
19 | Ticket Purchase | Auth: 2FA + backup codes | WORKING | AuthContext.tsx | Supabase Auth | YES | TOTP + recovery codes
20 | Scanner | QR code scanning (camera) | WORKING | html5-qrcode library | Back camera, 10 FPS | YES | Mobile + desktop
21 | Scanner | HMAC signature verification | WORKING | scanner-service.ts | SHA-256 timing-safe | YES | Anti-forgery protection
22 | Scanner | Offline ticket caching (IndexedDB) | WORKING | Dexie.js | IndexedDB cache | YES | 5-minute TTL, auto-refresh
23 | Scanner | Offline scan queue with retry | WORKING | offline-queue-service.ts | Exponential backoff | YES | 1s-60s, max 10 retries
24 | Scanner | Success/rejection overlays | WORKING | SuccessOverlay + RejectionOverlay | Full-screen UI | YES | Green/red with auto/manual dismiss
25 | Scanner | Audio + haptic feedback | WORKING | Scanner.tsx | Web Audio API | YES | Different sounds per result
26 | Scanner | Duplicate scan detection | WORKING | is_used field check | Database | YES | Shows previous scan info
27 | Scanner | VIP re-entry logic | WORKING | checkVipLinkedTicket RPC | vip_guest_passes | YES | Gold banner for re-entry
28 | Scanner | Manual ticket entry fallback | WORKING | ScannerInput component | Same processScan flow | YES | For damaged QR codes
29 | Scanner | Scan history (localStorage) | WORKING | Scanner.tsx | Last 10 scans | YES | Persistent across reloads
30 | Scanner | Check-in counter (real-time) | WORKING | CheckInCounter component | Supabase subscription | YES | X/Y format with live updates
31 | VIP System | Table creation per event (auto 8 tables) | WORKING | EventManagement.tsx | event_vip_tables | YES | 3 tiers: premium/front_row/standard
32 | VIP System | Custom pricing per table | WORKING | VIPSetupManager.tsx | Real price editing | YES | Saves immediately to DB
33 | VIP System | Guest pass generation (atomic) | WORKING | create_vip_reservation_atomic RPC | Transaction-safe | YES | QR tokens per guest
34 | VIP System | VIP scanner with offline queue | WORKING | VIPScanner.tsx | Separate queue | YES | 5s auto-sync
35 | VIP System | Reservation status tracking | WORKING | vip_reservations table | Real-time sub | YES | pending→confirmed→checked_in
36 | VIP System | Linked GA ticket check-in | WORKING | vip_linked_tickets table | Cross-table join | YES | Syncs GA ticket status on VIP check-in
37 | VIP System | Manual payment confirmation | WORKING | confirmPaymentManually() | Cash/card at door | YES | Generates passes after payment
38 | Event Creation | Full event CRUD with validation | WORKING | EventManagement.tsx | events table | YES | Name, date, time, venue, description
39 | Event Creation | Image upload to Supabase Storage | WORKING | event-image-service.ts | event-images bucket | YES | JPG/PNG/WebP/GIF, 5MB max
40 | Event Creation | Ticket type configuration | WORKING | ticket_types table | Per-event types | YES | Name, price, capacity per type
41 | Event Creation | Event sync to purchase site | WORKING | syncEvent() call | Cross-site sync | YES | Non-blocking sync on save
42 | Event Creation | Duplicate event detection | WORKING | handleSave validation | Same name+date check | YES | Prevents accidental duplicates
43 | Event Creation | Delete protection (ticket check) | WORKING | handleDelete validation | Checks for sold tickets | YES | Can't delete events with tickets
44 | Event Creation | Draft/published/archived status | WORKING | status field | State management | YES | published_at timestamp on publish
45 | Marketing Site | Homepage with video hero + parallax | WORKING | Framer Motion | Client-side | YES | Smooth animations
46 | Marketing Site | Event listing from Supabase | WORKING | Real-time subscription | events table | YES | Auto-updates on changes
47 | Marketing Site | Restaurant menu + cart | WORKING | Local state | Static menu data | YES | Cart works, but no payment
48 | Marketing Site | Security headers (CSP, HSTS) | WORKING | vercel.json | All 3 sites | YES | Comprehensive headers

## Potential Bloat
# | Area | Feature / Component | Why It Might Be Too Much | Recommendation | Action
1 | Dashboard | Monitoring: Circuit Breakers page | Nightclub owner doesn't need to see circuit breaker state diagrams | Remove from sidebar; keep in code for devs only | REMOVE from UI
2 | Dashboard | Monitoring: Rate Limits page | Owner doesn't need to see rate limit counters | Remove from sidebar; keep backend logic | REMOVE from UI
3 | Dashboard | Monitoring: Query Performance page | Database query profiling is a developer tool | Remove from owner-facing UI | REMOVE from UI
4 | Dashboard | Monitoring: Traces page | Distributed tracing spans are developer-only | Remove from owner-facing UI | REMOVE from UI
5 | Dashboard | Monitoring: Errors page | Error stack traces are for developers | Replace with simple 'System Health' indicator (green/yellow/red) | SIMPLIFY
6 | Dashboard | Monitoring: Metrics page | Raw application metrics too technical for nightclub | Replace with simple KPI dashboard card | SIMPLIFY
7 | Dashboard | Fraud Investigation page | Too complex; owner needs alerts, not investigation tools | Simplify to 'Security Alerts' with auto-block recommendations | SIMPLIFY
8 | Dashboard | Queue Management + Predictions | Queue prediction algorithms overkill for single-venue | Remove unless venue has 500+ capacity with actual queue issues | KEEP if needed
9 | Dashboard | Staff Scheduling page | Most nightclubs use GroupMe or paper schedules | Keep only if owner actually uses it; otherwise remove | ASSESS
10 | Dashboard | Customer Management page | CRM is overkill for nightclub; owners track VIPs mentally | Simplify to 'VIP Guest List' instead of full CRM | SIMPLIFY
11 | Dashboard | Device Management page | Most venues use 1-2 scanner devices | Keep if 3+ scanners; otherwise remove and auto-detect | ASSESS
12 | Dashboard | Notification Rules page | Complex rule builder; owner wants simple on/off toggles | Replace with simple notification preferences | SIMPLIFY
13 | Dashboard | Advanced Analytics - 6 tabs | Too many views; owner wants 3 numbers: money, attendance, performance | Consolidate to single page with 3 sections | SIMPLIFY
14 | Scanner | NFC scanning mode | Very few tickets use NFC tags in nightclub context | Keep as hidden option; don't show in main nav unless NFC detected | HIDE
15 | Scanner | ID Verification modal + photo capture | Useful but complex; most nightclubs check IDs manually | Keep for 21+ events; hide for general events | CONDITIONAL
16 | Scanner | Emergency Override system | Good safety feature but complex 4-digit PIN flow | Keep but simplify: single 'Override' button with owner fingerprint/face | SIMPLIFY
17 | VIP | Floor Plan visual editor | Static layout with no drag-drop; adds complexity without value | Either add real drag-drop or replace with simple numbered table list | FIX or REMOVE
18 | Scanner | Scan Speed Analytics | Scans per minute tracking is overengineered | Remove from UI; keep for backend diagnostics | REMOVE from UI
19 | Scanner | Battery Monitoring component | Tracks scanner device battery in real-time | Useful but could be a simple icon, not a dashboard section | SIMPLIFY
20 | All Sites | 50+ markdown docs in project root | Documentation sprawl across 80+ .md files | Consolidate into single docs/ folder with max 10 focused documents | CONSOLIDATE

## Summary
MAGUEY NIGHTCLUB LIVE - GSD SUMMARY
Overall Score | B+ (78-82%) | Near production-ready
Total Issues Tracked | 52
P0 Blockers | 12 | Must fix before launch
P1 High Priority | 26 | Fix within 2 weeks
P2 Medium | 9 | Fix within 1 month
P3 Nice to Have | 5 | Post-launch
Not Started | 52
In Progress | 0
Done | 0
Verified | 0 | Implementation verified
Verified Working Features | 48 | See 'What Works' sheet
Potential Bloat Items | 20 | See 'Potential Bloat' sheet
AREAS BREAKDOWN
Auth Issues | 7
Security Issues | 4
Scanner Issues | 10
Dashboard Issues | 6
VIP Issues | 3
Code Quality Issues | 4
Credentials Issues | 4
Auth Setup Issues | 3